Monster Mash 2009
ASAP:
Book DJ 
Submit Area Use for Cafeteria & Gym w/ the office


Chairpeople meet and come up with plan

Check out PTA closet, Monster Mash Box
Early Oct:

Contact Newsletter and have something put in for Monster Mash
Make Flyer/Volunteer Sign Ups

Copy & Distribute by first Friday in October
Put a large envelope in the office in PTA mail box for slips to be collected in


Check with Popcorn Person and verify they will have enough supplies for popcorn at Monster Mash


Plan the decorations and make them.
Week Prior:
Make Signs
Call Pizza Shop and pre-order
Contact and confirm all Volunteers/Bakers
Request checks from Treasurer for

~Start Up of $350 suggested for cafeteria bake sale
$200 Bake Sale -  5 rolls quarters 100 singles

$200 Front Door  - 100 singles, $100 broken up 20’s, 10’s, 5’s


~Check for DJ


~Check for Pizza

Day Before:

Confirm Order for pizza (2009 – 7 pizzas ordered and 20 slices were leftover at end)

Day Of:
Volunteers for bake sale drop off items at the main office throughout the day

Give DJ plan for contests and prizes
Pick up Pizza

Set up after school
Prizes for 2009 Monster Mash

	Contest
	Prize

	Limbo
	G.C.

	Hoola Hoop Kindergart.
	Bag

	Hoola  Hoop 1st Grade
	Bag

	Hoola  Hoop 2nd Grade
	Bag

	Hoola Hoop 3rd Grade
	Bag

	Hoola Hoop 4th Grade
	Bag

	Hoola Hoop 5th Grade
	Bag

	Costume Funniest
	G.C.

	Costume Scariest
	G.C.

	Costume Most Original
	G.C.

	Dance Contest
	G.C.

	Dance Contest
	G.C.


	Monster Mash '09 Set Up
	

	Café
	Popcorn - Start Popping

	
	Place tables

	
	Bake Sale brought in from Tim's office

	
	beverages

	
	Craft

	
	Face Paint

	
	Eating Area

	
	Cash Box

	Entrance
	Copy of volunteer sheet

	
	Tables & 3 Chairs

	
	Tally Sheets & Pencils

	
	Cash box

	
	Tablecloth & Decorations taped down

	Gym
	Chairs

	
	Hang Ballons on Wall

	
	Tape Boxes and Set Up

	
	Limbo Stick & Hoola Hoops

	Signs
	Hang Bats in Hallway

	
	Hang No Food Signs on Café & Gym Doors

	Kquad
	Chair

	
	Hanging Garland @ enterance of quad

	
	Spider Web w/spiders & bats

	
	CD Player

	
	Hang Balloons & Bats


